## April 15
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 5 |  |  |  |  | Kevin Kowalski | kkowal28@uic.edu
Week Of: 4/15/2019 |  |  |  |  | John Oshana | joshan3@uic.edu
[5 empty] | Frankie Ramirez | framir23@uic.edu
Team Number: 21 |  |  |  |  | Alec Thomas | athoma86@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Design cleint and server GUI | 1 | Kevin | n/a | Paper prototype GUI ideas based on features listed by John | Create rudimentary GUI for both client and server | Prototype not drawn/created until game features first listed out.
Implment game logic and specifications | 2 | John | n/a | Update team Google doc with all necessary features for clients and server | Begin developing game logic in client and server backend | Needs complete server backend to work on game logic
Create basic backend for supporting 4+ players | 3 | Frankie | n/a | Create basic backend for supporting 4+ simultaneous players | Update server backend to support features of game | Difficult to test without proper GUI
Help others on their action items | 4 | Alec | n/a | Work with the others as help is needed | Continue supporting team members where needed | Working on more than one action item